## Rating Sheet
RISK MATRIX
Likelihood | Consequences
| 1 | 2 | 3 | 4 | 5
| Insignificant | Minor | Moderate | Major | Catastrophic
A - Almost | M | H | E | E | E
Certain
B - Likely | M | H | H | E | E
C - Possible | L | M | H | H | E
D - Unlikely | L | L | M | H | H
E - Rare | L | L | M | H | H
Risk Matrix Legends
Rating | Safety |  | Health |  | Environment
1. Minor | Single minor injury to one person. First aid or no treatment required. No lost time. |  | Reversible health effects of minor concern only requiring minor first aid treatment. |  | Issues of non-continuous nature with promptly reversible impact or consequence (e.g. within shift). Low-level incident, site contained.
2. Moderate | Medically treated injury. Reversible injury. Does not lead to restricted duties. Less than 10 days lost time. |  | Reversible health effects of concern that results in medical treatment but does not lead to restricted duties. |  | Low-level incident, site contained. Short term reversible (e.g. within days).Issues of a non-continuous nature and minor impact and consequence.
3. Serious | Reversible injury or moderate irreversible impairment. |  | Severe but reversible health effects. Results in a lost time illness of less than 10 days. |  | Issues of a continuous nature - limited impact and consequence Incident resulting in some site contamination.Medium term recovery impact.
4. Major | Severe irreversible damage to one or more persons. Lost Time Injury greater than 10 days. |  | Severe and irreversible health effects or disabling illness. |  | Compliance issue with large fine, media attention. Serious harm not immediately recovered. Significant site contamination or off-site impact. Long term recovery.
5. Catastrophic | Fatality. Permanent disabling injuries. |  | Life threatening or permanently disabling illness. |  | Issues of a continuous nature with major long-term impact and potentially serious consequences
Rating | Descriptor |  |  | Description |  | Suggested Frequency
A | Almost certain |  |  | The event is expected to occur |  | Recurring event during the lifetime of a project / operation e.g. More than once per month.
B | Likely |  |  | The event will probably occur |  | Event that may occur frequently during the lifetime of a project / operation e.g. At least once per year.
C | Possible |  |  | The event should occur |  | Event that may occur during the lifetime of a project / operation e.g. Once in 3 years.
D | Unlikely |  |  | The event could occur |  | Event that is unlikely to occur during the lifetime of a project / operation e.g. Once in 10 years.
E | Rare |  |  | The event may occur only in exceptional circumstances |  | Event that is very unlikely to occur during the lifetime of a project / operation e.g. Once in 15 years.
Rating |  | Definition |  |  |  | Level of Involvement
Extreme |  | Cease work - No works shall be conducted until controls are implemented to reduce the risk level. Immediate formal risk assessment required. |  |  |  | The most senior person on site (Chief Executive Officer, Managing Director, General Manager) must review and approve risk control measures before allowing work to recommence.
High |  | Corrective action required.Normally permits required to perform work. Safe Work Procedure or Job Hazard Analysis is mandatory. |  |  |  | Mine Operator and / or Quarry Manager review required.
Moderate |  | Corrective action required. Job Hazard Analysis or Safe Work Procedure required.Safe Work Procedure or Job Hazard Analysis is mandatory. |  |  |  | Supervisor / Superintendent review required.
Low |  | Corrective action where practical.Take 5 risk assessment required. |  |  |  | Supervisor to manage by routine procedures at operational level.

## Register
Reference ID | Risk Description | Responsible Person | Likelihood | Consequence | Inherent Rating | Risk Control | Actions | Priority | Residual Risk
|  |  | A - Almost | C - Catastrophic | L - Low | Avoid |  |  | - Low
| What can happen? How can it happen? When can it happen? |  | Certain | Maj - Major | M - Medium | Accept |  |  | - Medium
|  |  | B - Likely | Mod - Moderate | H - High | Reduce |  |  | - High
|  |  | C - Possible | Min - Minor | E- Extreme | Retain |  |  | #NAME?
|  |  | D - Unlikely | I - Insigificant
E - Rare
STRATEGIC RISKS
1 | Loss of Government funding due to change in govt policy. | ALL | C - Possible | C - Catastrophic | E- Extreme | Reduce | Ensure Strategic Plan is reviewed and current. Maintain focus on sourcing alternate revenue streams. | Urgent | M - Medium
2 | Loss of Government funding due to VFC non-compliant activities. | MGMNT | C - Possible | C - Catastrophic | E- Extreme | Reduce | Complaince report to the Board at each meeting. Maintain complaince activities and policy updates as a management focus. | Critical | H - High
3 | Loss of Government funding due to poor governance practices by Directors | BOARD | C - Possible | Maj - Major | E- Extreme | Reduce | Undertake regular Board reviews and individual Director reviews annually | Critical | L- Low
4 | Reputational loss through poor business management leading to reduced funding. | ALL | B - Likely | Maj - Major | E- Extreme | Reduce | Ensure the best staff affordable are available. Ensure Directors with the right skill mix are selected. | I- Importamt | L- Low
5 | Lack of volunteers to provide services | ALL | C - Possible | Maj - Major | H - High | Reduce | Continual policy updtes, recruit suitakbe volunteers with management available to supervise appropriately. | Critical | M - Medium
6 | Loss of key personnel and inability to recruit suitable applicants | ALL | C - Possible | C - Catastrophic | E- Extreme | Avoid | Work towards being an employer of choice to attract and maintain staff | Critical | H - High
7 | Large competittors providing same services at lower rates | ALL | B - Likely | Maj - Major | E- Extreme | Accept | Have appropriate policy manuals in place and the focus remains on a community mindset | I- Importamt | L- Low
8 | Loss of operating space due to disaster | ALL | B - Likely | Mod - Moderate | H - High | Accept | Ensure a crisis management policy and plan is in operation. | I- Importamt | L- Low
9 | Loss of reputation to due cyber security breaches of personal and/or private information | ALL | B - Likely | C - Catastrophic | E- Extreme | Avoid | Ensure appropriate policies and procedures are followed and reviewed regularly. Ensure staff have the required skills to maximise the benefits of the systems in place. | Critical | E- Extreme
OPERATIONAL RISKS
10 | Financial fraud or mismanagement by staff | MGMNT | C - Possible | C - Catastrophic | E- Extreme | Reduce | Ensure correct policies in place identifying separation of duties. Minimum cash kept on hand. Board review of processes at least annually. | Critical | L- Low
11 | Loss of financial and other data due to poor backup procedures and file management. | MGMNT | C - Possible | Maj - Major | H - High | Reduce | Ensure the computer system is backed up daily and copies are kept of site. | Critical | L- Low
12 | Poor workplace practices causes staff and/or volunteer injury. | ALL | C - Possible | C - Catastrophic | E- Extreme | Avoid | Ensure new staff undertake an induction process. WHS report by management to the Board at each meeting. President contacted immediately should a major incident occur. | Critical | M - Medium
13 | Poor data management processes resulting in breach of private information. | MGMNT | B - Likely | Maj - Major | E- Extreme | Avoid | Ensure policies are in place. Cyber insurance investigated. | I- Importamt | L- Low
14 | Inability to recruit suitable staff and or volunteers. | ALL | B - Likely | C - Catastrophic | E- Extreme | Reduce | Undertake marketing activites to raise the profile of the organisation in the broadeer community | Critical | H - High
15 | Loss of operating capabiity due to cyber security breaches | MGMNT | B - Likely | C - Catastrophic | E- Extreme | Reduce | Secure Cyber Security Insurance over. Ensure Staff are trained to manage the security systems. Ensure all software backup procedures and firewalls are installed, curren and appliedt. | Critical | E- Extreme

## Charts
Trend analysis of Launceston VFC Risks with Residual Risk level of medium and above.
Risk Description |  | Residual Risk Rating | Rating June 22 | Rating Aug 22 | Rating Oct 22 | Rating Oct 22
1 | Loss of Government funding due to change in govt policy. | M - Medium | 2 | 2 | 2 | 2
2 | Loss of Government funding due to VFC non-compliant activities. | H - High | 3 | 2 | 2 | 2
3 | Lack of volunteers to provide services | M - Medium | 2 | 2 | 2 | 2
4 | Poor workplace practices causes staff and/or volunteer injury. | M - Medium | 2 | 2 | 2 | 2
5 | Inability to recruit suitable staff and or volunteers. | H - High | 2 | 2 | 3 | 3
6 | Loss of reputation to due cyber security breaches of personal and/or private information | E - Extreme | 4 | 4 | 4 | 4
7 | Loss of operating capabiity due to cyber security breaches | E - Extreme | 4 | 4 | 4 | 3
8 | Loss of key personnel and inability to recruit suitable applicants | H - High |  |  | 4 | 2
Rating for Chart
4 | Extreme
3 | High
2 | Medium
1 | Low