## Action List
Board of Management Action List
MEETING DATE | ACTION NO. | DESCRIPTION | DUE DATE | RESPONSIBLE OFFICER | STATUS
|  | Recruit Board members |  | Board & Mgmnt. | In progress and ongoing
|  | Directors to advise their interests to the President for the Standing Notice of Interests Register to be updated as required | Prior to next Board Meeting | Board | Ongoing
|  | Secretary to update Action Register | Prior to next Board Meeting | Secretary | Ongoing
2022-08-16 | 4.2.1 | Directors Ms Fiona Vanderbeek to review the Board of Management Policy and to be assisted in reviewing the Financial Management Policy by the Treasurer. |  | Director | In progress
2022-12-20 | 3.3.3 | GM and Amanda McEvoy to redraft Mission and Values in January, for discussion at next meeting. | January | GM/Amanda McEvoy | In progress
| 4.1.4 | Amanda McEvoy to redraft minutes for approval by ARC at next meeting | Prior to next ARC meeting | Amanda McEvoy | In progress
2023-02-28 | 3.1 | President to draft advertisement for new directors | ASAP | President
| 3.1 | Amanda McEvoy to circulate skills matrix and collate responses to identify skills rqeuired of new directors | ASAP | Amanda McEvoy
| 3.3.1 | Secretary to circulate a penultimate draft of Strategic Actions Plan chart | ASAP | Secretary | Complete
| 3.3.1 | All board members to respond to penultimate draft of Strategic Actions Plan chart | One week after receipt | Board | Complete
| 3.3.1 | Secretary to compile final draft of Strategic Actions Plan chart | Prior to next Board Meeting | Secretary | Complete
| 3.3.2 | GM and Amanda McEvoy to produce final draft of Mission and Values review for discussion and approval | Prior to next Board Meeting | GM/Amanda McEvoy
| 4.1.5 | Secretary to send Amanda McEvoy template for agenda and minutes | ASAP | Secretary | Complete
| 5.1 | Secretary to add annual leave dates to Board calendar | Prior to next Board Meeting | Secretary | Complete
| 5.1 | Secretary to send ARC members copy of Board agenda item calendar | ASAP | Secretary | Complete
| 5.2 | Amanda McEvoy and GM to work on marketing plan for recruitment of volunteers | Prior to next Board Meeting | GM/Amanda McEvoy

## Completed Actions
Board of Management Completed Action List
MEETING DATE | ACTION NO. | DESCRIPTION | DUE DATE | RESPONSIBLE OFFICER | STATUS | REMOVED
|  | Sub-let Premises |  | Manager | Completed | BM 15/02/2022
|  | Source additional funding |  | All | On going | BM 19/04/2022
|  | Succession Planning |  | Board | On going | BM 19/04/2022
|  | Annual Performance Review for Board and Manager | 2021-07-31 | Board | Completed
|  | Billing accuracy |  | Manager | Completed
| 4 | A&RC to review and advise on MV due for replacement | 2021-07-13 | Treasurer | Completed | BM 19/10/2021
|  | Website Development |  | Manager | Completed &On going
|  | Initiate Conversations with CCT |  | Board | Completed. BM Jan 19 2021 | BM 20/04/21
|  | Annual Fee Increase |  | Manager | Completed. BM Feb 16 2021 | BM 20/04/21
2020-12-07 | 1 | Additional information sort by both VFC and CCT on posible merger. |  | Board & Mgmnt. | Overtaken by events. Remove | BM 20/04/21
2020-12-07 | 2 | New Action List to be created |  | Manager | Completed BM20 April | BM 20/04/21
2021-01-19 | 2 | Bookkeeper to be invited to meet with A&RC. |  | Treasurer | Completed.Meeting held | BM 20/04/21
2021-01-19 | 1 | Terms of reference for new Audit & Risk Committee be written. |  | Secretary | Completed. BM Feb 16 2021 | BM 20/04/21
2021-02-16 | 1 | Members to sign new Position Descriptions |  | Board | Completed | BM 20/04/21
2021-02-16 | 2 | Decision to be finalised on whether to restructure or merge with CCT. |  | Board | Completed | BM 20/04/21
2021-02-16 | 3 | A&RC to report on the review of the MYOB reconciliation |  | Treasurer | Completed | BM18/05/2021
2021-03-16 | 1 | A&RC to draft the 21-22 Budget ASAP |  | Treasurer | Completed refer BM May Item 3.2 | BM18/05/2021
2021-03-16 | 2 | Members to review the terms of the Employsure proposal | 2021-04-20 | Board | Completed. BM April 20 2021 | BM 20/04/21
2021-03-16 | 3 | Members to review the updated Policies and Procedures manual | 2021-04-20 | Board | Completed. BM April 20 2021 | BM 20/04/21
2021-04-20 | 1 | A&RC to report on budget review | 2021-05-18 | Treasurer | Completed refer BM May Item 3.2 | BM18/05/2021
| 2 | Mgr to report on staff review | 2021-05-18 | Manager | Completed | BM 20/07/2021
| 3 | Strategic Plan to be completed | 2021-04-30 | Board & Mgmnt. | Completed Refer BM May Item 4 | BM18/05/2021
2021-04-30 | 1 | Secretary to create a Board Calendar and add relevant items for discussion at May Board Meeting | 2021-05-18 | Secretary | Completed refer BM May Item 5.1
| 2 | Manager to progress the restructure process and report at next Board Meeting. | 2021-05-18 | Manager | Completed | BM 20/07/2021
| 3 | Strategic Planning Committee to meet to progress the finalisation of the Plan | 2021-05-12 | Board & Mgmnt. | Completed refer BM May Item 4 | BM 18/05/2021
2021-05-18 | 2.3.1 | Secretary to add a due date of July to ‘Annual Performance Review for Board and Manager’ and amend due date of ‘Report on staff review’ by Manager to July | 2021-06-15 | Secretary | Completed | BM 15/06/2021
| 2.3.2 | Manager to arrange for Director search to be removed from the Seek Volunteer web site. | 2021-06-15 | Manager | Completed | BM 15/06/2022
| 3.1.3 | Treasurer to change account name ‘Client fees charged’ to ‘Client Contributions’ and ‘Other Grants in Advance’ to ‘Residual BLCW Fund’ | 2021-06-15 | Treasurer | Completed | BM 15/06/2023
| 3.1.4 | Treasurer to review Annual Leave and Long Service Leave Provisions to ensure the provisions are correct for 30 June 2021. | 2021-06-30 | Treasurer | Completed for audit | BM 15/06/2024
| 3.1.5 | Treasurer to review the Salary sacrifice account to determine the nature of its balance as well as the Board Governance and Suspense expense accounts in the P&L | 2021-06-15 | Treasurer | Completed for audit | BM 15/06/2025
| 3.1.6 | Treasurer to contact the auditor to request details of the VFC’s ATO Integrated Balance Account so as to assist in reconciling the related GST accounts in the Balance Sheet. | 2021-06-15 | Treasurer | Completed | BM 15/06/2026
| 3.2.7 | Manager to complete a working draft of the budget and provide to the AR&C in three weeks so that the budget may be finalised for the next Board Meeting. | 2021-06-15 | Manager | Completed | BM 15/06/2027
| 3.3.8 | Directors to provide photos and bio of 150-word limit to Manager for uploading to the web site prior to next Board Meeting. | 2021-06-15 | Board | Completed | BM 19/10/2021
| 4.2.9 | Secretary to make the amendments to the KPI’s and Responsibilities as discussed and present to the next Board Meeting for approval | 2021-06-15 | Secretary | Completed refer MB June Item 4.1 | BM 19/10/2022
| 5.1.10 | Secretary to make the amendments to the Board Calendar as discussed. | 2021-06-15 | Secretary | Completed refer BM June Item 5.1 | BM 19/10/2022
2021-06-15 | 2.3.1 | Secretary to amend the Register with Actions ‘Completed’ or ‘In progress’ as agreed |  |  | Completed | BM 19/10/2022
| 3.1.1 | Treasurer to investigate the makeup of the $70k Term Deposit funds. |  |  | Completed | BM 19/10/2022
| 3.3.1 | Manager to email a complete copy of the Employsure report to Directors |  |  | Completed | BM 19/10/2022
| 3.3.2 | Secretary to arrange for a Circulating Resolution on the approval of progression of the Employsure recommendations. |  |  | Completed | BM 19/10/2022
| 3.3.3 | Secretary to organise the official Declaration of Notice of Meeting for the AGM to all Members giving 21 clear days’ notice. |  |  | Completed | BM 19/10/2022
| 3.3.4 | President and Secretary to meet with Manager to finalise her Employment Agreement. |  |  | Completed | BM 19/10/2022
| 3.3.5 | Manager to provide a copy of the proposed organisational structure for the next Board meeting. |  |  | Completed | BM 19/10/2022
| 4.1.1 | Manager to provide a copy of the final Strategic Plan to members for the next Board meeting. |  |  | Completed | BM 15/02/2022
| 4.2.1 | President to write a Thank You letter to the applicant noting the Board’s decision. |  |  | Completed | BM 19/10/2030
| 4.2.2 | President to review suitable director marketing skills ads for inclusion in a revamped website ad for new director |  |  | Overtaken by events | BM 19/10/2031
| 5.1.1 | Secretary to make the amendments to the Board Calendar as discussed. |  |  | Completed | BM 19/10/2022
2021-10-19 | 3.1.1 | The transaction entry for the period in Depreciation of $25,735.78 to be investigated by the Treasurer and Manager. |  | General Manager | Completed | BM 15/02/2022
| 3.1.2 | The budget in MYOB be revised to reflect the period in which actual income and expenses occur. |  | Board & Mgmnt. | Completed refer BM August 16 Item 5.2
| 3.2 | The President to telephone the Assistant Treasurer to discuss the Role moving forward. |  | President | Completed | BM 15/02/2022
| 3.3.1 | GM authorised to request the MYOB consultant to review and update leave liabilities in the Balance Sheet during his visits. |  | General Manager | Overtaken by events
| 4.1.1 | Manager to email the fleet options for future leases and possible payout figures at 30 June 2022 |  | General Manager | Completed | BM 15/02/2022
| 4.1.2 | Vice-President to prepare a paper on proposed Motor Vehicle policy for the December Board Meeting noting the routine replacement of motor vehicles and the lease vs purchase options. |  | Vice-President | Completed | BM 15/02/2022
| 4.1.3 | Manager to create new version of Manager’s Report for trial for the December Board Meeting. |  | General Manager | Completed | BM 19/04/2022
| 4.1.4 | Manager to email information on unit cost fees increases in preparation for a Board Out of Session Circulating Resolution |  | General Manager | Completed | BM 15/02/2022
| 4.1.5 | Manager to make amendments to the MOU correcting the rent inclusive amount to exclusive of GST and rent increases to be based on the percentage Hobart CPI. |  | General Manager | Completed | BM 15/02/2022
| 4.1.6 | Manager to formally note any WHS instances, including motor vehicle accidents and report to the Board. |  | General Manager | Completed | BM 15/02/2022
2021-12-14 | 3.1.1 | The GM to contact the Auditor to endeavour to gain access to past copies of MYOB data files for use by VFC. |  | General Manager | Completed | BM 15/02/2022
| 3.1.2 | The GM to create the required MYOB contingency accounts in the Balance Sheet. |  | General Manager | Completed | BM 15/02/2022
| 3.2.1 | The President to telephone the Assistant Treasurer to discuss his future priorities and advise of the Board’s recommendation. |  | President | Completed | BM 15/02/2022
| 3.2.2 | The President to contact the AICD and other organisations to begin the Director recruitment process so as to increase the VFC Director capacity by an extra three places at least |  | President | Completed | BM 15/02/2022
| 3.3.1 | GM authorised to request the MYOB consultant to review and update leave liabilities in the Balance Sheet during his visits. |  | General Manager | On going - agreed BM April 22 to move to completed
| 3.4.1 | GM to email a copy of the proposed ACNC Annual Report to the Directors for any comment. |  | General Manager | Completed | BM 15/02/2022
| 3.4.2 | GM to review and investigate the Home Maintenance Service and report to the Board. |  | General Manager | On going - agreed BM April 22 to move to completed
| 4.1 | Directors to provide the GM with proof of vaccination for VFC records and government returns as soon as possible – and prior to next February board meeting. |  | Board & Mgmnt. | Completed | BM 15/02/2022
| 5.2.1 | The President to update the Calendar with the inclusion in February of a full review of the Strategic Plan. |  | President | Completed | BM 15/02/2022
| 5.2.2 | The President to undertake individual Director Reviews during the month of June 2022. |  | President | Completed refer BM August Item 4.1
2022-02-15 | 2.3.1 | GM to arrange a time to review the 2022-23 MYOB budget with the President | Prior to 19/04/2022 | General Manager | Overtaken by events
| 2.3.2 | Directors advised to consider Co-vid 19 booster vaccinations as these were likely to be mandated for the sector. |  | Board & Mgmnt. | Completed
| 3.3 | President to arrange the creation of the Charts in preparation for December 21 Board Meeting. |  | President | Completed
| 3.1.1 | GM to investigate and report on the detail of the Volunteer Cost accounts at next Board meeting |  | General Manager | Completed for June 22BM
| 3.1.2 | In future Management to collate and provide copies of Financial Reports to the Treasurer for review one week prior (at least) to each Board Meeting | Prior to 19/04/2022 | Management | Completed
| 3.1.3 | Clearing accounts and Suspense Accounts to be reconciled by Management, prior to reports being provided to the Treasurer | Prior to 19/04/2022 | Management | Completed
| 3.1.4 | President to investigate with the Commonwealth Bank whether she was required to complete any further documentation for the new Bank Account | 2022-02-18 | President | Completed
| 3.3.1 | GM to circulate a copy of the Home Maintenance Grant to Directors | Prior to 19/04/2022 | General Manager | Completed
| 3.3.2 | In future GM to email a copy of proposed external Reports to the President and Vice-President as well as the Treasurer to ensure availability of Directors for their review and comment. |  | General Manager | Completed
| 3.3.3 | President to provide a Compliance Report template to the GM for consideration of its incorporation in the future GM Board Report. | Prior to 19/04/2022 | President | Completed
| 4.2 | GM to discuss with the President any variations or updates required to the Risk Register prior to each Board Meeting so the Register may be updated prior to meetings. | Prior to 19/04/2022 | General Manager | Completed
| 4.3.1 | Vice-President to contact the Hon Jo Palmer MLC to endeavour to arrange a meeting with her, the President, Vice-President and GM to discuss LVFC and what it does | 2022-02-18 | Vice-President | Completed
| 4.3.2 | GM to present the collection of stories composed to date (for marketing purposes) on the services provided to our clients |  | General Manager | Replaced by April 3.2.4
| 4.4.1 | GM to investigate and activate, if possible, the utility of Zoom technology for future Board Meetings | Prior to 19/04/2022 | General Manager | Completed
| 4.4.2 | President to advise Directors on progress with the proposed Director candidate | Prior to 19/04/2022 | President | Completed
| 5.2.1 | The President to update the Calendar with the AGM date | Prior to 19/04/2022 | President | Completed
2022-04-19 | 2.3.1 | Treasurer to arrange payment of Bonus to GM as soon as practicable. | ASAP | Treasurer | Completed
| 2.3.2 | Management to investigate the President’s application for a Commonwealth Bank toggle to facilitate authorisation of electronic bank transfers for the Association’s payments. | after AGM | Management | Complete
| 3.1.1 | President to finalise the Director profiles and email to GM |  | President | Completed
| 3.1.2 | Treasurer to investigate secure access for Board Papers other than via email. |  | Treasurer | Overtaken by events
| 3.1.3 | GM to investigate the possibility of a secure Board only section of the LVFC web site for Board documents |  | General Manager | Complete
| 3.2.1 | President to provide a copy of the amendments to Ms Vanderbeek and Mr John Byrne for compilation in Track Changes and Review for completion for presentation at the June Board Meeting. |  | President | Completed refer BM August 16 Item 4.2
| 3.2.2 | GM to investigate whether LVFC funders are required to give pre-approval to any Rule amendments |  | General Manager | Completed refer BM August 16 Item 4.2
| 3.2.3 | GM to provide a brief to at least three web developers for them to submit proposals for updating and enhancing the web site. |  | General Manager | Completed refer BM August 16 Item 4.3
| 3.2.4 | GM to investigate the collation digitally of the hard copy good news stories already collected. |  | General Manager | Complete
| 4.1 | GM to forward the period’s Financial Reports to the Treasurer and Vice-President at 1.5 weeks prior to each Board Meeting to enable a thorough review |  | General Manager | Completed and ongoing
| 4.2 | GM to forward the completed 2022-23 Budget to the Treasurer and Vice President (Cc to the President) so that they may review and discuss the Budget prior to the next Board Meeting. |  | General Manager | Overtaken by events
| 4.3 | President to add the risk of cyber security breaches to the Risk Register. |  | President | Completed
| 5.2.1 | President to add Director reviews to the June meeting calendar. |  | President | Completed
| 5.2.2 | GM to email Zoom URLs for each remaining Board Meeting to each Director. | Prior to June 21 2022 meeting | General Manager | Completed and ongoing
2022-08-16 | 2.1 | The GM to email a copy of the staff annual review templates to the President |  | General Manager | Completed
| 2.2 | The President and Vice-President to liaise with GM on a suitable date and time for her annual review. |  | Board | Completed
| 3.1 | Directors to advise their Interests to the President for the Standing Notice of Interests Register to be formally completed |  | Board | Completed
| 3.3.1 | President to update the Action Register. |  | President | Completed
| 3.3.2 | Treasurer to follow up on Board Portals for the Board Papers. |  | Treasurer | Overtaken by events
| 3.3.3 | President to provide GM with a list of items to be uploaded to the Board only section of the LVFC website once the firewall technology update is completed. |  | President | Completed
| 4.1.1 | Directors to complete the DIN application and advise the President of the number. |  | Treasurer | Complete
| 4.1.2 | Directors to finalise their evaluation forms by Friday 26th August. |  | Board | Completed
| 4.1.3 | President to contact Michelle Swallow to discuss travel costs and confirm acceptance of the proposal. |  | President | Completed
| 4.1.4 | President to contact Simone Zell to advise the Board’s decision on her training proposal. |  | President | Completed
| 4.2.2 | Director Ms Amanda McEvoy to investigate the possibility of the Launceston City Council sponsoring the purchase of uniforms and to advise the GM |  | Director | Completed
| 4.3 | GM to email a copy of the Draft Marketing Plan to Director Ms Amanda McEvoy for her comments and suggestions |  | General Manager | Completed
| 4.4 | GM to place the Notice of Meeting in the local paper and advise members through the newsletter. |  | General Manager | Completed
| 5.1.1 | Management to investigate an anomaly with the wages coding in the month of July and report to the Treasurer |  | Management | Completed
| 5.1.2 | Copies of 2022 Financial Statements to be forwarded to the proposed Audit & Risk Committee members and the President for review prior to any Circulating Resolution being passed via email authorising the signing of the accounts by the Treasurer. |  | General Manager | Completed
| 5.3 | President to update the Risk Register and present at the next Board Meeting prior to the A&R Committee taking over responsibility of the Register |  | President | Completed
| 6.1 | GM to prepare a report on what policies and procedures are in place to mitigate risks to our clients from services provided by staff and volunteers. | Dec Board Mtg | General Manager | Complete
2022-10-18 | 2.1 | Directors to advise their interests to the President for Standing Notice of Interests Register to be updated as required |  | Board | Complete/Ongoing
| 2.3 | Secretary to update the Action Register. |  | Secretary | Complete
| 2.4 | GM to record Christine Fordham as a member of LVFC |  | General Manager | Complete
| 3.1 | President to table a report on Board evaluations at next meeting | Dec Board Mtg | President | Complete
| 3.2 | GM to circulate updated COVID safety plan once ACEOC update announced |  | General Manager | Complete
| 3.2 | Timing of ARC and Board meetings to be reviewed for 2023 meeting calendar | Dec Board Mtg | Board and GM | Complete
| 3.2 | GM to provide data to Funding Indexation Project |  | General Manager | Complete
| 3.2 | GM to note changes to bank account authorities and signatories |  | General Manager | Complete
| 3.3 | Board to review Strategic Actions Plan Chart and match Objectives and Activities | Dec Board Mtg | Board | Complete
| 3.3 | Secretary to circulate copy of Strategic Actions Plan |  | Secretary | Complete
| 4.1 | Treasurer to circulate copy of AGFA report to Board for approval |  | Treasurer | Complete
2022-12-20 | 3.3.1 | President to circulate a draft of proposed revisions to Strategic Actions Plan Chart | Prior to next Board Meeting | President | Complete
| 3.3.2 | All Board members to review draft Strategic Actions Plan and provide their own suggested amendments for discussion at next meeting | Prior to next Board Meeting | Board | Complete
| 3.3.4 | Strategic Objective (d) be amended to “To follow best practice governance principles, strive for operational excellence and ensure thorough succession planning for the Board and management” |  | Secretary | Complete
| 5.1.1 | President to compile schedule of calendar dates for 2023 meetings of ARC and Board | January | President | Complete
| 5.1.2 | Secretary to compile Board meeting agenda item calendar | January | Secretary | Complete

## Sheet2
Krishna
All
Board
Board & Mgmnt.
Management
Secretary
Treasurer
Carolyn
President
Assistant Treasurer
General Manager
Glen
Vice-President
John
Treasurer/ Assistant Treasurer
Kevin
Director
Eric